## Sheet1
ATTACHMENT 3 SCHEDULE OF PAYMENTS/PAYABLE MILESTONES TOA #2018-### Project Title
Phase | Milestone | Deliverable Title | Due Date | Program Funding | Cost Share
1 | 1 | Project Plan | 2019-01-30 | 5000 | 5000
1 | 01a | Technology Transfer Plan | 2019-01-30 | 0 | 0
1 | 01b | Kick-off Meeting Minutes | 2019-01-30 | 0 | 0
1 | 2 | Quarterly Report 1 | 2019-03-20 | 0 | 0
1 | 3 | Initial Design | 2019-04-15 | 10000 | 10000
1 | 4 | Quarterly Report 2 | 2019-06-30 | 0 | 0
1 | 5 | Survey | 2019-08-15 | 2500 | 2500
1 | 6 | End of Phase Meeting Minutes | 2019-09-20 | 0 | 0
|  | Phase 1 Totals |  | 17500 | 17500
2 | 7 | Design Update | 2019-09-30 | 10000 | 5000
2 | 8 | Quarterly Report 3 | 2019-10-20 | 0 | 0
2 | 9 | Initial Prototype Build | 2019-10-31 | 100000 | 100000
2 | 10 | Quarterly Report 4 | 2019-12-20 | 0 | 0
2 | 11 | Testing | 2020-01-30 | 100000 | 100000
2 | 12 | Finalize Build | 2020-02-15 | 200000 | 200000
2 | 13 | Quarterly Report 5 | 2020-03-20 | 0 | 0
2 | 14 | Final Workshop | 2020-05-30 | 50000 | 50000
2 | 15 | Final Report and Project Results Template | 2020-06-20 | 0 | 0
|  | Phase 2 Totals |  | 460000 | 450000
|  |  | Project Total | 477500 | 467500
PLEASE NOTE:
1 | The above format/template must be followed when developing the TOA Attachment 3, to ensure consistent and accurate tracking of deliverables and invoices.
2 | All milestone numbers must be entered as shown above (01, 02, 03, . . . ). Sub-milestones, as described below, must be entered as shown above (01a, 01b, . . . ).
3 | Any deliverables with multiple files (ex., There are three separate files associated with Milestone 01 -- Project Plan, Technology Transfer Plan, and Kick-off Meeting Minutes) MUST be broken out as separate sub-milestones, as shown above.
4 | Per the TOA, Technical and Business Reports are required to be submitted on a calendar quarterly basis. ALL Quarterly Reports MUST be included in the Attachment 3, as shown above, if Quarterly Reports are designated as "no cost," enter "$0" under Funding and Cost Share.
SAMPLE