## Sheet1
ATTACHMENT 3 SCHEDULE OF PAYMENTS/MILESTONES DELIVERABLES Task Order #TBD (Enter Project Name)
Phase | Milestone | Deliverable Title | Due Date | Program Funding | Cost Share
1 | 1 | Project Management Plan | 2019-01-30 | 5000 | 5000
1 | 01a | Kick-off Meeting Minutes | 2019-01-30 | 0 | 0
1 | 01b | Kick-off Meeting Presentations | 2019-01-30 | 0 | 0
1 | 2 | Quarterly Report 1 | 2019-03-20 | 0 | 0
1 | 3 | Initial Design | 2019-04-15 | 10000 | 10000
1 | 4 | Quarterly Technical Review Minutes | 2019-05-15 | 0 | 0
1 | 5 | Quarterly Report 2 | 2019-06-20 | 0 | 0
1 | 6 | Survey | 2019-08-15 | 2500 | 2500
1 | 7 | Quarterly Technical Review Minutes | 2019-09-10 | 0 | 0
1 | 8 | Quarterly Report 3/Phase 1 Report | 2019-09-30 | 0 | 0
|  | Phase 1 Totals |  | 17500 | 17500
2 | 9 | Design Update | 2019-09-30 | 10000 | 5000
2 | 10 | Initial Prototype Build | 2019-10-31 | 100000 | 100000
2 | 11 | Quarterly Report 4 | 2019-12-20 | 0 | 0
2 | 12 | Testing | 2020-01-30 | 100000 | 100000
2 | 13 | Finalize Build | 2020-02-15 | 200000 | 200000
2 | 14 | Quarterly Report 5 | 2020-03-20 | 0 | 0
2 | 15 | Final Workshop | 2020-05-30 | 40000 | 50000
2 | 16 | Final Report and Project Results Summary | 2016-06-20 | 0 | 0
|  | Phase 2 Totals |  | 450000 | 455000
|  |  | Project Total | 467500 | 472500
PLEASE NOTE:
1 | 1. The above format/template must be followed when developing the Task Order Attachment 3/Milestone Schedule, to ensure consistent and accurate tracking of deliverables and invoices
2 | 2. All milestone numbers must be entered as shown above (01, 02, . . . ). Sub-milestones, as described below, must be entered as shown above (01a, 01b, . . . )
3 | 3. Any deliverables with multiple files (ex., There are 3 separate files associated with Milestone 01 -- Project Plan, Technology Transfer Plan, and Kick-off Meeting Minutes) MUST be broken out as separate sub-milestones, as shown above.
4 | 4. Per the Task Order, Technical and Business Reports are required to be submitted on a calendar quarterly basis, on the 20th of March, June, September and December. ALL Quarterly Reports MUST be included in the Attachment 3/Milestone Schedule -- as shown above, if Quarterly Reports are designated as "no cost," enter "$0" under Funding and Cost Share
5 | This document (SCHEDULE OF PAYMENTS/PAYABLE MILESTONES) will be Attachment 3 to the Task Order awarded under the existing Task Order Agreement(s) between ATI and the Prime Contractor
SAMPLE