## Slide 1: FIBER OPTIC TESTING ENHANCEMENT FOR COST REDUCTION FOLLOW-ON
Improvement to FO Testing for significant manpower and schedule reduction benefits
Project Update
12/02/2020
Presented by:
Felipe Guadalupe (KITCO Fiber Optics)

## Slide 2: FIBER OPTIC TESTING ENHANCEMENT FOR COST REDUCTION FOLLOW-ON
NSRP Project Task Order: | 2019-472
KITCO Project: | NSRP-2019-472
Sponsor: | Advanced Technology International 315 Sigma Drive Summerville SC 29486
Sponsor TPOC: | Nick Laney (843) 760-3485 nicholas.laney@ati.org
Sponsor Contracts: | Scott Leecock (843) 760-3226 scott.leecock@ati.org
Contractor: | KITCO Fiber Optics 5269 Cleveland Street Virginia Beach, VA 23462
Principal Investigator: | Dan Morris (757) 216-2220 dan.morris@kitcofo.com
KITCO Fiber Optics Contracts: | Holly Andrews (757) 216-2301 holly.andrews@kitcofo.com
Project Manager: | Felipe Guadalupe 757 216-2226 felipe.guadalupe@kitcofo.com
Project Technical Rep (PTR): | Jason Farmer (228) 935-7573 jason.farmer@hii-ingalls.com
Data Category B: | Data developed partially with funding from project participants that was not charged to a government contract and partially with government funding.
Distribution Statement: | Limited Distribution Authorized to U.S. Shipyards, NSRP Program Representatives, and Government Agencies.

## Slide 3: Project Overview
This project will focus on the validation of the previous project laboratory findings thru evaluation of optical testing on a new construction VCS submarine, USS New Jersey (SSN-796). The intent is to investigate the potential for Fiber Optic Testing Enhancement for Cost Reduction by evaluating the commercial practice of using an Optical Time Domain Reflectometer (OTDR) to replace the Optical Loss test Set (OLTS) and Optical Return Loss Meter (ORLM) in performance of MIL-STD-2042 Part 6 required shipboard installations tests that must be performed at various stages during the construction process, minimizing the number of tests and the time to perform the separate testing. In addition, the OTDR test results will provide enhanced data that is not currently captured resulting in reduced time for system acceptance and identification of potential faults for expedited troubleshooting and repair during construction.

## Slide 4: Project Status Summary
Project suspended through March 2021 due to COVID-19.
Based on the latest forecasted schedule, NNS has indicated testing on New Jersey is likely to occur between June and Sept 2021.
It is anticipated that project will make four (4) three (3) day visits to NNS between Starting April 2021 and may last thru September 2021.
NSRP project funding expires 3/31/2021. The ECB did increase our funding ceiling by 10K.
NSRP Task Order 2019-472-001 Mod 2 is in the process of review for submission.

## Slide 5: Project Schedule
 | Oct 19 | Nov 19 | Dec 19 | Jan 20 | Feb 20 | Mar 20 | Apr 20 | May 20 | Jun 20 | Jul 20 | Aug 20 | Sep 20 | Oct 20 | Nov 20 | Dec 20
1) Kick-Off Meeting and Project Plan Development |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
2) Procurement of Test Equipment and Materials |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
3) Testing of FO Circuit Leads onboard SSN-794 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
4) Testing Result Comparison Analysis |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
5) Project Suspended |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Suspended
Suspended
 | Jan 21 | Feb 21 | Mar 21 | Apr 21 | May 21 | Jun 21 | Jul 21 | Aug 21 | Sep 21 | Oct 21 | Nov 21 | Dec 21
1) Project Suspended |  |  |  |  |  |  |  |  |  |  |  | 
2) Restart Project |  |  |  |  |  |  |  |  |  |  |  | 
3) Procurement of Test Equipment and Materials |  |  |  |  |  |  |  |  |  |  |  | 
4) Testing of FO Circuit Leads onboard SSN-796 |  |  |  |  |  |  |  |  |  |  |  | 
5) Testing Result Comparison Analysis |  |  |  |  |  |  |  |  |  |  |  | 
2021 Schedule

## Slide 6: Procured Equipment
The Two (2) MAX-OLSTNAVY-NSRP1 (EXFO-945) were delivered on 02/27/2020 to NSWC Dahlgren Division, Code A31 for evaluation
Procured Equipment List |  |  | 
Manufacturer | Description | QTY | Date
EXFO-945 | Light Source, SM & MM (with EF Launch)/Power Meter /ORLM | 2 | 21-Feb-20
EXFO iOLM | OTDR, SM and MM (with EF Launch)/Power Meter | 2 | 20-Mar-20
*Not Yet Procured Equipment List |  |  |  |  | 
M85045/16-01 (MM) |  |  | M85045/16-02 (SM) |  | 
Part # | Description | QTY | Part # | Description | QTY
KFO 60810-EXP | MQJ ST/4 CH Recpt 1 meter 6877804-08 | 2 | KFO 60830-EXP | MQJ ST/4 CH Recpt 1 meter 6877804-08SME | 2
KFO 60510 | MQJ ST/ST 1 meter 6877804-05 | 4 | KFO 60530 | MQJ ST/ST 1 meter 6877804-05SME | 4
0705-5610 | MQJ ST/LC 1 Meter 6877804-15 | 4 | KFO-11923 | MQJ ST/LC 1 Meter 6877804-15SME | 4
N/A | MQJ ST/4CH Recpt 50 meter (Special Cable) | 2 | N/A | MQJ ST/4CH Recpt 50 meter (Special Cable) | 2
N/A | MQJ ST/8 CH Recpt 50 meter (Special Cable) | 2 | N/A | MQJ ST/8 CH Recpt 50 meter (Special Cable) | 2
*Note: The not yet procured equipment is awaiting configuration verification based on
HII-NNS input regarding all planned project test links

## Slide 7: Project Outstanding Tasks
Tasks/Items that still need to be accomplished include:
Identification of potential additional paths (to include fiber and connector configurations)
Presentation of this information to NSWCDD to verify their concurrence that the FO paths identified will allow for appropriate analysis of test result data in order to draw acceptable conclusions
Identification of project required MQJ’s and test leads
Procurement of required test leads
Identification of reasonable and acceptable project site visits dates to conduct the required testing (assumes 3 to 4 visits of 3 to 4 days each)
Verification that all parties can support such dates and MQJs will be ready
Actual site visits for project testing – Project team records project test data (assumes 3 to 4 visits of 3 to 4 days each)
Testing by NNS of the same paths and transference of test data to compare to project test data
Analysis of project data
Final report drafting
Review by all team members
Final report finalization

## Slide 8: Current Deliverables Schedule
The Base TOA (2019-472) was executed on 09/17/2019. MOD 1 updated POP to 10/11/2019 – 09/15/2020 and MOD 2 updated POP to 02/15/2020 – 09/15/2020. MOD 2 updated to extended POP from 9/17/2020 through 10/31/2021.
Deliverable Schedule |  | 
Deliverable | Team Member(s) | Due Date
Project/Test plan & Schedule | KITCO Fiber Optics - Dan Morris | 11/15/2019
Quarterly Report #1 | KITCO Fiber Optics - Dan Morris | 12/15/2019
List of Material Procured | KITCO Fiber Optics - Dan Morris | 12/1/2019
Project Status Brief to ETP | KITCO Fiber Optics - Dan Morris HII-NNS - Dave White/Dave Ellis | ~12/10/2019
Quarterly Report #2 | KITCO Fiber Optics - Dan Morris | 3/15/2020
Project Status Brief to ETP | KITCO Fiber Optics - Dan Morris/Felipe Guadalupe HII-NNS - Dave Ellis | ~3/10/2020
Project Suspended due to COVID-19 |  | 
Quarterly Report #3 | KITCO Fiber Optics - Dan Morris/Felipe Guadalupe | 4/15/2021
Quarterly Report #4 | KITCO Fiber Optics - Dan Morris/Felipe Guadalupe | 7/15/2021
Summary Report of all Project Visits and Tests conducted | KITCO Fiber Optics - Dan Morris/Felipe Guadalupe | 9/1/2021
Final Report with Recommendation | KITCO Fiber Optics - Dan Morris/Felipe Guadalupe | 10/31/2021

## Slide 9
Questions???